## DSDM products - RASCI-V matrix
DSDM products | Business sponsor | Business visionary | Technical Co-ordinator | Project Manager | Business analyst | Team leader | Solutions developers | Solutions testers | Business ambassador | Technical advisor | Business advisor | Workshop Facilitator | Agile coach | Support Manager
| Project level |  |  |  | Solutions development team |  |  |  |  | Supporting
Key | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Accountable — ultimately answerable
Responsible — who does the work
Support — resources allocated to Responsible
Consulted — subject matter experts
Verifier — checks it meets the acceptance criteria
Informed — kept up to date with progress
Pre-project
—1.1 Terms of Reference | A |  |  | V | V
Feasibility
2.1 Feasibility assessment | A / C | V / C | V / C | V / C | R | C | C | C | C | C | C
— Outline business case | A / C | V / C | V / C | V / C | R | C | C | C | C | C | C
— Risk assessment | A / C | V / C | V / C | V / C | R | C | C | C | C | C | C
— Outline solution | A / C | V / C | V / C | V / C | R | C | C | C | C | C | C
—2.1.1 Feasibility prototype (optional) |  | A | C | V |  | R | S | S | S | C | C
2.2 Outline plan | A | V | V | R | C
— 2.2.1 Project approach questionnaire (PAQ) | A / C | V / C | V/ C | R | C | C | C | C | C | C | C
Foundations
3.1 Business foundations (business case / vision) | A / C | V / C | V / C | V / C | R |  |  |  | C |  | C
3.2 Prioritised requirements list (PRL) |  | A / C |  | V | R | V | V | V | V / C |  | C
3.3 Solution Foundations
— 3.3.1 Business area definition (BAD) |  | A |  | V | R | V |  |  | C |  | C
— 3.3.2 System architecture definition (SAD) |  |  | R | A | C | V | V
— 3.3.3 Development approach definition (DAD)
——3.3.3.1 Solution review strategy |  | A | A | S | R | V | C | C | C | C | C
——3.3.3.2 Solution development standards |  |  | R | A | C | V / C | V / C | V / C | V / C | C | C
— 3.3.4 Solution prototype |  | A | A | V | C | R | S | S | S |  | C
3.4 Management foundations | A | V | V | R |  | V | [6 empty] | C
3.5 Delivery plan | V | A / V | V | R / V | V | V / C | V / C | V / C | V / C | V | V
3.6 Delivery Control Pack
— 3.6.1 Risk Log | A / C | V / C | V / C | R | C | C | C | C | C | C | C
— 3.6.2 Change control records | A | V | V | A | R | V |  |  | C |  | C
— 3.6.3 Periodic reports | A | C | C | R |  | C
Exploration and engineering
4.1 Evolving solution |  | A | A | V | S | R | S | S | S | C | C
—4.1.1 Business model (optional) |  | A | V | V | R | C | C | C | C
—4.1.2 Design model (optional) |  | A | A | V | S | R | S | S | S | C | C
—4.1.3 Capability / technique prototype (optional) |  | A | A | V | S | R | S | S | S | C | C
— 4.1.4 Business user documentation (as required) |  | A | A | V | S | R | S | S | S | C | C
— 4.1.5 Support documentation (as required) |  | A | A | V | S | R | S | S | S | C | C
— 4.1.6 Deployable solution |  | A | A | V | S | R | S | S | S | C | C
4.2 Solution assurance pack
— 4.2.1 Solution review records |  | A | A | V | S | R | S | S | S | C | C
— 4.2.2 Business testing pack
—— 4.2.2.1 Business acceptance test plans |  | A | A | V | C | C |  | S | R
—— 4.2.2.2 Business test scenarios |  | A | A | V | C | C |  | S | R
—— 4.2.2.3 Business test data |  | A |  | A | V |  | C | V | R |  | C
—— 4.2.2.4 Business test records |  | A |  | A | V |  | C | V | R
— 4.2.3 Technical testing pack
—— 4.2.3.1 Technical test plans |  |  | A | V |  | C |  | R
—— 4.2.3.2 Technical test scenarios |  |  | A | V |  | C |  | R
—— 4.2.3.3 Technical test data |  |  | A | V |  | C |  | R
—— 4.2.3.4 Technical test records |  |  | A | V |  | C |  | R
4.3 Deployment plan | A | V | V | R | C | S | C | C | C
—4.3.1 Benefits realisation plan | A / V | R |  |  | C
4.4 Timebox plan |  |  | A | A |  | R / V | V / C | V / C | V / C
4.5 Timebox review record |  | A | A | V | C | R | S | S | S
Deployment
5.1 Deployed solution | A | V | V | V |  | R | S | S | S | C | C |  |  | A
5.2 Project review report
— 5.2.1 Increment review record | A | V |  | R | C | C |  |  | C
— 5.2.2 Benefits enablement summary | A | A | V | R | C | C |  |  | C |  | V
— 5.2.3 End of project assessment | A | V | V | R | C | C
Post-project
6.1 Benefits assessment | V / C | R |  |  | C |  |  |  | C |  | C